## 5YP_Aug_2023
|  | MaxDuino Version => | 1 | 1.1 |  | 1.2 | [6 empty] | 2
5YP Planning Year |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5
Calendar Year |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Section | Objective | Tech | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Platform | Easy to assemble with as many standard parts as practical. | 2 layer TH PCB | bar: 2023 Q3
Power Supply | Robust and usable with most layouts accessory power | Flexible | bar: 2023 Q3
SBC | Functional but Inexpensive | NANO 3.x | 2024 Q3: Migrate to ESP32?
I2C | Drive OLED displays | Yes | bar: 2023 Q3
RS485 | Communications and growth | Yes | 2023 Q3: Mod
MP3 | Animations | Yes | bar: 2023 Q3
NeoPixel | Diagnositics | single SM 2812B | 2023 Q3: Mod
I/O | Sensor inputs, servo outputs | Up to 15 | bar: 2023 Q3
DCC Decode | Stationary accessory decode | Yes | bar: 2023 Q1; 2023 Q3
SPI | Communications and growth | In Ver 2.0 | 2024 Q3: Add ?
Canbus | MERG CBUS intergration | In Ver 2.0 | 2024 Q3: Add ?
Now

## RAIL_Aug_2023
RAIL
When | Item | Who | Status
2023 Q3 | Gather MERG feedback and areas for improvement Publish this plan as a starting point and receive comments. | AL | Closed
2023 Q3-Q4 | Redesign PCB to R1.2 adding headers for Proposal 1, 2 & 3. Also address deficiencies list 1 and 2 Develop an initial appliance like application. Test for enthusiasm. By Year end this needs to be a team effort. (or you get what it is ) | AL | Closed
2024 Q1-Q4 | Promote within MERG including forming a working team to steward this roadmap. Develop several appliance like applications. Test for thoughts on MaxDuino education. (curriculum, format delivery etc) |  | New
2024 Q4 | Go-No-Go decision re V2 - full on redesign PCB to R2 with a NANO-ESP32 processor, adding WifI plus dual core 32 bit processing at espense of 3.3v I/O |  | Investigating
Note on A1: Alan Lomax: RAIL = Rolling Action Item List

## Current Proposals
Proposals | [5 empty] | Proposed Version | Status
No | 5YP Colour | Description | Impact if Accepted | Impact if Rejected | Next Step if Proceed
1 |  | Add SPI (Header) to MaxDuino | SPI devices can be accomodated. Requires redesign of MP3 to use other pins. Loss of some GPIO header pins Significant testing of software serial on new pins. | None (No SPI) | Determine header pins and order. Update Schem, PCB, Docs | 2 | Investigating
2 |  | Add CANBUS (via Header) to MaxDuino | CBUS devices can be accomodated via external board. (Requires SPI above) | None (No CBUS) | Determine header pins and order. Update Schem, PCB, Docs | 2 | Investigating
4 |  | Change SBC to an ESP32 solution (full PCB redesign) | Technically more capable. Adds native WiFi networking (inc WebServer) Adds language choices. Needs All new applications Needs All new documentation | No immediate change. Potential obsolecence of NANO | Weigh pros and cons carefully before proceeding. ESP32 module or native chip? | 2 | Investigating
3 |  | Modify so that 'S' pin of D4 header can be supplied from Dout of NeoPixel OR direct from D4 when no on board NP is installed. This is tied to deficiency #2 | On board NP is always index 0, External NP start at index 1 (on D4 header) Build time decision with on board NP | Current design has on board NP at index 0 and first external NP is also starting at address 0 (overlapping). Restricts usage of on board NP and impacts animations. | Update Schem, PCB, Docs | 1.2 | Closed | SCH modified PCB Artwork Complete Test articles made Testing Complete
5 |  | Modify RS485 so that DE/RE are driven from separate pins to allow for ICSP. This is tied to deficiency #1 | Allows for ICSP One more GP I/O pin will serve a dual purpose. | Remove NANO for reprogramming if RS485 must noe be affected. | Update Schem, PCB, Docs | 1.2 | Closed | ditto
Note on C3: Alan Lomax: SPI: 10 (SS) or Chip Select, 11 (MOSI), 12 (MISO), 13 (SCK).

## Current Deficiencies
Deficiency List
Item | Applies to | Known Deficienices | How To Reproduce Deficiency | Workaround / Alternate | Impact | Probability | Proposed Remedy | Consequences of Remedy | Decision | Status
1 | V1.1 | RS485 DE and RE are driven by same pin. Both cannot be disabled as is needed for ICSP of Arduino. | Kisnet with multiple Arduinos. Use USB to program one and it disrupts all communications. | Always use header pins and socket the Nano. Reprogram NANO only out of circuit | Disrupts communications | 100% | Redesign SCH and PCB to add second pin. Standard pins to use are D2/D3. | Knock on effect for D3 (Thr DCC decoding pin.) | Include in V1.2 | Closed
2 | V1.1 | Both the on board Neopixel (NP) and the IO header pin D4 are driven from Arduino pin 4 directly. Using index 0 both NP will blink at same time. | With on board NP installed add external NP string to header D4. Run NP test program. Two NP's will blink (both are index 0) | Do not install on board NP. | Diagnostic output will impact animation displays. | 100% | Drive IO signal pin (D4 header) from Dout of the on board NP | Use of D4 requires on board NP or some sort of bypass arrangement | Include in V1.2 | Closed
Note on C8: On Aug 10 2023 on the MERG forum John Purbick Wrote: But I've got my own RS485 system, which I've talked about using the name KISnet (and it's going to be in the next Journal). It has one Arduino designated as master, and when that one makes a transmission, each of the others transmits in turn. There's no need for a computer. So this network could be buzzing away, and you might have connected up the USB port on one unit in order to re-program it. I hope we'll agree that you can't have the RX function active during programming, because it swamps out the USB RX. So you'd have to be in TX mode during programming, which would totally disrupt traffic on the bus, maybe with your unit being reprogrammed transmitting at the same time as another unit. It would be better to disable both RX and TX, and that's something you can only achieve by setting the DE pin high, and the RE pin low. Hence the need for 4 lines dedicated to communication, not 3. But perhaps you're not thinking of a multi-processor system at all, and the MaxDuino is always the master of the bus. If that's the case, maybe there's no harm done if it makes uncontrolled transmissions during re-programming. You'd just have to be sure that those transmissions can't stimulate other devices on the bus to take any damaging actions.

## Validations
Deficiency Status | Proposal Decisions | RAIL Status
New
Investigate | Insufficient Data | Investigating
Confirmed | Accepted | In Progress
Plan Developed | Rejected | Response TBC
In Design | Recycle (with comments) | Closed
In Manufacturing |  | Defer
Testing
Closed