## RAIL_Aug_2023
RAIL
When | Item | Who | Status
2023 Q3 | Gather MERG feedback and areas for improvement Publish this plan as a starting point and receive comments. | AL | In Progress
2023 Q3-Q4 | Redesign PCB to R1.2 adding headers for Proposal 1, 2 & 3. Also address deficiencies list 1 and 2 Develop an initial appliance like application. Test for enthusiasm. By Year end this needs to be a team effort. (or you get what it is ) |  | New
2024 Q1-Q4 | Promote within MERG including forming a working team to steward this roadmap. Develop several appliance like applications. Test for thoughts on MaxDuino education. (curriculum, format delivery etc) |  | New
2025 Q1-Q2 | Go-No-Go decision re V2 - full on redesign PCB to R2 with an ESP32 processor, adding WifI plus dual core 32 bit processing. |  | Defer
Note on A1: Alan Lomax: RAIL = Rolling Action Item List

## 5YP_Aug_2023
|  | MaxDuino Version => | 1 | 1.1 |  |  | 1.2 | [5 empty] | 2
Year |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5
|  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Section | Objective | Tech | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Platform | Easy to assemble with as many standard parts as practical. | 2 layer Through Hole PCB
Power Supply | Robust and usable with most layouts accessory power | Flexible
SBC | Functional but Inexpensive | NANO 3.1 | 2025 Q3: Migrate to ESP32?
I2C | Drive OLED displays | Yes
RS485 | Communications and growth | Yes
MP3 | Animations | Yes
NeoPixel | Diagnositics | single SM 2812B | 2023 Q3: Mod
I/O | Sensor inputs, servo outputs | Up to 15
DCC Decode | Stationary accessory decode | Yes
SPI | Communications and growth | No | 2023 Q3: Add
Canbus | MERG CBUS intergration | No | 2023 Q3: Add

## Current Proposals
Proposals
No | 5YP Colour | Description | Impact if Accepted | Impact if Rejected | Next Step if Proceed
1 |  | Add SPI (Header) to MaxDuino | SPI devices can be accomodated. Will require redesign of MP3 software serial | None (No SPI) | Determine header pins and order. Update Schem, PCB, Docs
2 |  | Add CANBUS (via Header) to MaxDuino | CBUS devices can be accomodated via external board. (Requires SPI above) | None (No CBUS) | Determine header pins and order. Update Schem, PCB, Docs
3 |  | Modify so that 'S' pin of D4 header can be supplied from Dout of NeoPixel OR direct from D4 when no on board NP is installed. | On board NP is always index 0, External NP start at index 1 (on D4 header) Build time decision with on board NP | Current design has on board NP at index 0 and first external NP is also starting at address 0 (overlapping). Restricts usage of on board NP and impacts animations. | Update Schem, PCB, Docs
4 |  | Change SBC to an ESP32 solution (full PCB redesign) | Technically more capable. Adds native WiFi networking (inc WebServer) Adds language choices. Needs All new applications Needs All new documentation | No immediate change. Potential obsolecence of NANO | Weigh pros and cons carefully before proceeding. ESP32 module or native chip?

## Current Deficiencies
Deficiency List
Item | Applies to | Known Deficienices | How To Reproduce Deficiency | Workaround / Alternate | Impact | Probability | Proposed Remedy | Consequences of Remedy | Decision | Status
1 | V1.1 | RS485 DE and RE are driven by same pin. Both cannot be disabled as is needed for ICSP of Arduino. |  | Always use header pins and socket the Nano. Reprogram NANO only out of circuit | [5 empty] | Investigate
2 | V1.1 | Both the on board Neopixel (NP) and the IO header pin D4 are driven from Arduino pin 4 directly. Using index 0 both NP will blink at same time. | With on board NP installed add external NP string to header D4. Run NP test program. Two NP's will blink (both are index 0) | Do not install on board NP. | Diagnostic output will impact animation displays. | 100% | Drive IO signal pin (D4 header) from Dout of the on board NP | Use of D4 requires on board NP or some sort of bypass arrangement | Include in V1.2 | Plan Developed

## Validations
Deficiency Status | Proposal Decisions | RAIL Status
New
Investigate | Insufficient Data | Investigating
Confirmed | Accepted | In Progress
Plan Developed | Rejected | Response TBC
In Design | Recycle (with comments) | Closed
In Manufacturing |  | Defer
Testing
Closed